## Slide 1
NATIONAL / DOMESTIC / LOCAL STANDARDS
Plan of Action to be Int’l Team
9.
Team Field EX
(USAR Operations)
11.
Mentor Report to Regional Chair
2.
Approval of Focal Point + Government+ Donor
8.
Training to International Light Standards
12.
Regional INSARAG EQ EX/CLASS-EX
(Management/ Command Post)
(Mentor or EXCON Checklist Feedback)
14.
CLASS-EX
(Management)
3.
Develop Operational Capacity according to Guidelines/Int. Light Handbook (External Help if needed)
7.
Procure additional Equipment
13.
Learn from Reg. INSARAG EQ EX/CLASS-EX
15.
Recognition
5.
(Re)write SOP’s
6.
Adapt the Organization of the Team
16.
INTERNATIONAL LIGHT USAR TEAM
4.
Select Mentor (approved by FCSS) support for Development Process and Quality Assurance
NO
YES
1.
Start Quality Assurance Process
10.
Submission of Portfolio of Evidence
NO
YES
TOPICS

## Slide 2
INSARAG recommends building National USAR Capability prior to commencement of Int. Light USAR Team Capability
Check the operational capability of the Team based on 5 functions. Assessed by the mentor according to Int’l LT Checklist
Mentor Report to Regional Chair
(including additional development required from FieldEX and PoE)
INSARAG relies on network of (National) focal points for approval to commence
Define training gaps
Optimize training program for international deployment
Implement the new training program
Team Management participate in an INSARAG formatted International Response Exercise
(Reg EQ EX/ IEC/ IER/ MODEX/ Classified Team Annual EX)
Assessment of Management team will take place in a CLASSEX to improve the efficiency and international cooperation of teams. (1 Management Classifier for max. 2 Teams)
Team has to define its own operational capability
(Eg. Search)
Define equipment gaps
Optimize logistics cache for international deployment
Establish equipment manifest
Learn, Review and adopt learning from INSARAG formatted International Response Exercise
A certificate of classification will be provided. (INSARAG considers giving a generic badge with no year/no classification level if necessary.)
Standard Procedures are needed for International Deployment in a USAR Response as per the Guidelines
Define functional gaps
Optimize integration of functions
Establish new team structure
INTERNATIONAL LIGHT USAR TEAM
Teams are advised to run this process in a learning environment and select a mentor to succesfully complete the QA process
NO
YES
INTERNATIONAL LIGHT USAR TEAMs require this Quality Assurance Process
Provide the Complete Portfolio of Evidence according to V2 Manual C to Regional Chair
NO
YES
Explanation

## Slide 3
NATIONAL / DOMESTIC / LOCAL STANDARDS
Plan of Action to be Int’l Team
Team Field EX
(USAR Operations)
Mentor Report to Regional Chair
Approval of Focal Point + Government+ Donor
Training to International Light Standards
Regional INSARAG EQ EX/CLASS-EX
(Management/ Command Post)
(Mentor or EXCON Checklist Feedback)
CLASS-EX
(Management)
Develop Operational Capacity according to Guidelines/Int. Light Handbook (External Help if needed)
Procure additional Equipment
Learn from Reg. INSARAG EQ EX/CLASS-EX
Recognition
(Re)write SOP’s
Adapt the Organization of the Team
INTERNATIONAL LIGHT USAR TEAM
Select Mentor (approved by FCSS) support for Development Process and Quality Assurance
NO
YES
Start Quality Assurance Process
Submission of Portfolio of Evidence
NO
YES
INSARAG recommends building National USAR Capability prior to commencement of Int. Light USAR Team Capability
Check the operational capability of the Team based on 5 functions. Assessed by the mentor according to Int’l LT Checklist
Mentor Report to Regional Chair
(including additional development required from FieldEX and PoE)
INSARAG relies on network of (National) focal points for approval to commence
Define training gaps
Optimize training program for international deployment
Implement the new training program
Team Management participate in an INSARAG formatted International Response Exercise
(Reg EQ EX/ IEC/ IER/ MODEX/ Classified Team Annual EX)
Assessment of Management team will take place in a CLASSEX to improve the efficiency and international cooperation of teams. (1 Management Classifier for max. 2 Teams)
Team has to define its own operational capability
(Eg. Search)
Define equipment gaps
Optimize logistics cache for international deployment
Establish equipment manifest
Learn, Review and adopt learning from INSARAG formatted International Response Exercise
A certificate of classification will be provided. (INSARAG considers giving a generic badge with no year/no classification level if necessary.)
Standard Procedures are needed for International Deployment in a USAR Response as per the Guidelines
Define functional gaps
Optimize integration of functions
Establish new team structure
INTERNATIONAL LIGHT USAR TEAM
Teams are advised to run this process in a learning environment and select a mentor to succesfully complete the QA process
INTERNATIONAL LIGHT USAR TEAMs require this Quality Assurance Process
Provide the Complete Portfolio of Evidence according to V2 Manual C to Regional Chair
ANIMATED