INSARAG AEME - key activities in 2019[[1]](#footnote-1)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Dates** | **Activity** | **Expected outcome** | **Location** | **Member responsible** |
| March | Distribution of a questionnaire along all members of the region on the use of INSARAG methodology | understand level of knowledge and use of INSARAG methodology |  | Italy |
| June | Set up a Technical Supporting Group with representatives of all countries from the region and organize a workshop where to promote the NAP and identify a process on how to implement it | guiding document on national USAR team accreditation system to make the process better understood and managed in practice | France | France / Turkey? |
| June | Identify a list of countries in the region still not part of INSARAG network and test a twinning program with available member | Improve the resilience in the member of the region |  | Italy |
| April | Training for structural engineer |  | Italy (Poggioreale) | Germany |
| ?? | Collect information on project/meeting/workshop/training planned by region's country and share it; liaise with EU (DG ECHO) which is monitoring different development activities at least in the ENP countries | map existing programs and funding opportunities for capacity development activities |  | Other MEAE country? |
| June | Identify together with EU Commission a disaster-prone country from EU neighborhood countries where to organize an EU funded exercise | Increase cooperation between countries |  | Italy |
| July | Define ad hoc twinning programs between AEME classified teams and countries of other regions who are exposed to natural as well man-made risks | Increase cooperation between countries |  | Italy |
| July | MODEX Poggioreale invitation to participate with skeleton team to AEME countries | Increase cooperation between countries |  | Italy |
| July | UCC ToT |  | Siberia |  |
| August | Organize a workshop on recent national experience from different countries (GENOA) | Share best practices, build network |  | Italy |
| October/ November | Design and test a course for INSARAG classified team management on the UN system of response (UNDAC cluster system, WHO EMT, CIMIC) |  | Country to identify | France +?? |
|  |  |  |  |  |
| June | Elaborate and distribute a questionnaire along all members of the region in order to understand the available experiences “beyond the rubble”; introduction of standard for purification capacity in Husar team linking with the goal "Advancing Flexible Assistance" - based on questionnaire, useful to map activities "beyond the rubble" and also to list kinds of non-earthquake disasters where USAR may be useful and link it with international risk assessment |  |  | France and Poland |
| Beginning in March | Recommend to INSARAG FP to meet WHO EMT nation FP |  |  | France |
| September | INSARAG AEME Regional earthquake exercise |  |  | Azerbaijan |
| October | AEME Regional Meeting |  |  | Italy |
| October | Identify best practices on how to approach to disabilities during USAR operation (during AEME meeting) | Improvement of INSARAG guidelines |  | Italy |
| October | Presentation of results EU co-funded project EASER on “barrier effect” during USAR operation and first step of new project BELICE (during AEME meeting) | Sharing of results |  | Italy |
| October | Discuss on the need of guidelines for USAR teams on how to operate on buildings with cultural heritage value (during AEME meeting) | Improvement of INSARAG Guidelines |  | Italy |
| October | Discussion on the use of helicopter for USAR deployment (during AEME meeting) | Improvement of INSARAG Guidelines |  | Italy |
|  | Discussion about 2020-2025 strategy (during AEME meeting) |  |  | Poland? |

1. The list actually includes only activities promoted by Italy France and Poland however all Regional Member has the opportunity to contribute or add activities. [↑](#footnote-ref-1)